## Mkt Tasks
| Go-Live Date | TCI - MARKETING TASKS
Task Ref # | Cutover/Post-Go-Live | Category | Phase* | Task ID | Task | Responsible Business Unit | Business Owner | Target Start Date (T minus Go-Live) | Content Draft | Final To Compliance | Compliance Approval | Release For Production | Deploy to Test | Marketing Sign Off | Deploy Live Date/Time | Take Down Date/Time | Current Status | Task Description | Notes
|  | TCI | I |  | UI Page Validation (Content & URLs)
|  | TCI | I |  | Validate Delivery of Triggered Comms & CTA links/buttons within
|  | secure.pml.com |  | 1 | App Page 1 Content | [12 empty] | Content edits to return to application login screen
|  | secure.pml.com |  | 2 | Log In Error Message (No Active App Found) | [12 empty] | No current active application can be found in the system
|  | secure.pml.com | IV | 3 | Validate 301 redirect for subdomain
|  | Sitecore | II | 4 | Update: Sitecore Kiosk Start Page
|  | Sitecore | IV | 5 | Update: Login Page | [12 empty] | New page to direct applicants/customers to the right platform matching their intent.
|  | Sitecore | IV | 6 | Update: FAQs | [12 empty] | Update content.
|  | Sitecore | IV | 7 | Update Military Allotment | [12 empty] | Update content.
|  | Sitecore | IV | 8 | Update: Allotment Authorization Page | 10.3.17 | 10.4.17 | 10.10.17
|  | Sitecore | IV | 9 | Update: Contact Us | [12 empty] | Update content.
|  | Sitecore | IV | 10 | Update: Online Account Access | [12 empty] | Update content.
|  | Sitecore | IV | 11 | Update: Welcome Page | [12 empty] | Update content.
|  | Sitecore | IV | 12 | Application Status Right Rail | [12 empty] | Update content.
|  | Sitecore | IV | 13 | FAQ Page/Local App Pages: Left Nav MyAccount/Utility Nav | [12 empty] | Update content.
|  | Sitecore | IV | 14 | Post App Redirect: review/update as needed | [12 empty] | Update content.
|  | Sitecore | IV | 15 | Update redirects: MyAccount & Log In Links/Buttons | [12 empty] | Update links
|  | Sitecore | IV | 16 | Update: Application URL on all applicable pages/features/right rails/heroes | [12 empty] | Updated homepage and right rail modules (new design, content, functionality)
|  | Sitecore | IV | 17 | Update: RTA links
|  | Sitecore | IV | 18 | Native Mobile App Sitecore Page Updates | Marketing | Randy Freese | 4.24.17 | [9 empty] | Update content/links.
|  | Sitecore | IV | 19 | Google Tag Manager Activation
|  | Customer Communications | I | 20 | Auto Protection Sales Electronic Fulfillment Kit
|  | Customer Communications | I | 21 | Auto Protection Talking Points
|  | Customer Communications | I | 22 | Instant Funding Talking Points
|  | Customer Communications | IV | 23 | Email List Development Process | [12 empty] | List (new creation process) complete and ready for new lists downloads by 10.25.
|  | Customer Communications | IV | 24 | Active Applicant Pre-Launch Alert Email Send 1 | [12 empty] | Email all applicants in the AM with an active application to encourage completion/booking by midnight on 1.17. Alert applicants that applications not booked are still valid but will not be processed until 1.22..18 (when system goes live).
|  | Customer Communications | IV | 25 | Active Applicant Pre-Launch Alert Email Send 2 | [12 empty] | Same as above in the AM with addition of active apps since send on 1/15.
|  | Customer Communications | IV | 26 | Active Applicant Post-Launch Email | [12 empty] | Email all applicants with an open/active application to alert them that they can log in to check the status of their application and complete the process.
|  | Customer Communications | IV | 27 | IVR Messaging Post Launch | [12 empty] | Restore IVR messaging back to originat state
|  | Lead Source | I | 28 | Tracking Code Creation | [12 empty] | Pause pre application take down. Restart post all systems up.
#REF! | Cutover | Lead Source | I | 29 | Validate Tracking | Marketing | Randy Freese | [10 empty] | Pause in alignment with application take down. Restart with app launch.
#REF! | Cutover | Lead Source | I | 31 | Reporting | Marketing | Randy Freese | [10 empty] | Pause in alignment with application take down. Restart with app launch.
#REF! | Cutover | Lead Source | II | 30 | Tracking Code Creation | Marketing | Randy Freese | [10 empty] | Email affiliate partners to notify of system down time. To be sent via Outlook.
|  | Lead Source | II | 32 | LPO Team Member Desktop | [12 empty] | Email affiliate partners to notify of system up. To be sent via Outlook.
|  | Lead Source | II | 31 | Validate Tracking Links On LPO Screens
|  | Lead Source | II | 33 | Validate Tracking
|  | Lead Source | II | 32 | Reporting
|  | Lead Source | III | 34 | Tracking Code Creation
|  | Lead Source | III | 33 | Tracking Implementation
|  | Lead Source | III | 35 | Validate Tracking
|  | Lead Source | III | 34 | Reporting
|  | Lead Source | IV | 36 | Tracking Code Creation
|  | Lead Source | IV | 35 | Tracking Implementation - Paid Search
|  | Lead Source | IV | 37 | Tracking Implementation - Email
|  | Lead Source | IV | 36 | Tracking Implementation - Affiliates
|  | Lead Source | IV | 38 | Tracking Implementation - Display
|  | Lead Source | IV | 37 | Tracking Implementation - Website
|  | Lead Source | IV | 39 | Validate Tracking
|  | Lead Source | IV | 38 | Validate Tracking - Affiliates
|  | Lead Source | IV | 40 | Reporting
|  | SOPs |  | 41 | Marketing Project Management
|  | SOPs |  | 42 | Website Change Management
*Phase I: Outbound Phone App LV
*Phase II: LPO Takes Applications
*Phase III: Inbound Phone App LV
*Phase IV: Route Web Traffic to TCI Portal