## All Combined
Project | Job | Task | Current Status | Marketing Review | Draft to TCI | Internal Review Due Date | Internal Review Complete | Send To Compliance | Compliance Approved | Final to TCI | Notes
Fields/Rules/Integration
| Collection fields | Define by section/page | In Progress |  | 2016-03-31
| Messaging & advancement rules | Define for fields | In Progress
| 3rd party integration | Impact to consumer interface
| Phone App Flow | Need to define | Pending
Consumer Interface [Portal]
| Sitemap (diagram of all potential consumer interface pages) |  | Complete
| Wireframes (pending TCI development process) |  | Cancelled
| Application domain | Need to define
| Website brand design | Determine look/feel | Complete
| Page layout |  | In progress
Page by page content development
| Start Application | Send to TCI for development | In Review | √ | 2016-03-31 | 2016-04-15
| Complete Application | Send to TCI for development | In Review | √ | 2016-03-31 | 2016-04-15
| Decision Waiting | Send to TCI for development | In Review | √ | 2016-04-07 | 2016-04-15
| Confirm Identity | Send to TCI for development | In Review | √ | 2016-03-31 | 2016-04-15
| Loan Offers | Send to TCI for development | In Development
| Debt Protection | Send to TCI for development | In Development
| Auto Protection | Send to TCI for development | In Development
| Loan Disbursement (ACH, Click-to-Brick, In-Office) | Send to TCI for development | In Review | √ | 2016-04-07 | 2016-04-15
| Loan Repayment | Send to TCI for development | In Review | √ | 2016-03-31 | 2016-04-15
| Loan Summary | Send to TCI for development | In Development
| Loan Documents (eOriginal Signing Room] |  | Researching
| Loan Recap | Send to TCI for development | In Development
| Info Needed/Upload | Send to TCI for development | In Review | √ | 2016-04-07 | 2016-04-15
| Upload Confirm | Send to TCI for development | In Review | √ | 2016-04-08
| Application Stop (fail presescreen rules) | Send to TCI for development | In Review | √ | 2016-04-07 | 2016-04-15
| Application Denial (adverse action messaging) | Send to TCI for development | In Review | √ | 2016-04-07 | 2016-04-15
| Return To App [authentication] | Send to TCI for development | In Review | √ | 2016-03-31 | 2016-04-15
| No Decision | Send to TCI for development |  | √
| No Response | Send to TCI for development |  | √
| Session Ended | Send to TCI for development |  | √
| Utility Nav | Send to TCI for development | In Development
| Contact Us or Call? | Send to TCI for development | In Development
| FAQs | Send to TCI for development | In Development
| Header/Footer Content | Send to TCI for development | In Development
Consents/Disclosures
| TCPA [TBD] |  | Pending
| Privacy Policy [link in app/footer] | Send to TCI for development | In Progress
| Terms of Use [link in app/footer] | Send to TCI for development | Researching
| Electronic Disclosures [link in app] | Send to TCI for development | In Progress
| eSign Statement Disclaimer |  | Pending
| eSign Consent |  | Pending
| eStatement Enrollment Agreement |  | Pending
Project | Job | Task | Current Status | Marketing Review | Draft toTCI | Internal Due Date | Internal Review Complete | Send To Compliance | Compliance Approved | Final to TCI | Notes
Consent Management
| Collection of consents (online, voice phone, retail applicants) |  | Pending
| Storage of consents |  | Pending
| User interface tool to update consent |  | Pending
| Processes to align all outbound communication efforts against consents |  | Pending
Consumer Communications
| Triggered Communications (Origination) | Determine CP outbound comm triggers | Complete
Consumer Portal Content
| Partial Application (1 day) | Develop content | In Progress
| Partial Application Reminder (3 days) | Develop content | In Progress
| Completed Application (immediate) | Develop content | In Progress
| Info Requested (1 day) | Develop content | In Progress
| Info Requested (3 days) | Develop content | In Progress
| Info Requested (5 days) | Develop content | In Progress
| Info Requested (25 days) | Develop content | In Progress
| Stips Cleared/Application Approved | Develop content | In Progress
| Additional Info Needed | Develop content | In Progress
| Approved/Not Booked (1 day) | Develop content | In Progress
| Approved/Not Booked (3 days) | Develop content | In Progress
| Approved/Not Booked (5 days) | Develop content | In Progress
| Approved/Not Booked (25 days) | Develop content | In Progress
| Application Denied w Adverse Action (immediate) (Consumer) | Develop content | In Progress
| Application Denied w Adverse Action (immediate) (Retail) | Develop content | In Progress
| Documents Ready For Signature (1 day) | Develop content | In Progress
| Document Signing Reminder (3 days) | Develop content | In Progress
| Document Signing Reminder (5 days) | Develop content | In Progress
| Document Signing Reminder (25 days) | Develop content | In Progress
| Customer Welcome Email (Consumer) | Develop content | In Progress
| Customer Welcome Email (Retail) | Develop content | In Progress
| Triggered Communications (Core) | Determine core outbound comm triggers | Researching
| Paid in full | Develop content | Researching
| Other (TBD) | Develop content | Researching
Retail Online
| Branding (match Sitecore experience) | Review as developed | In Progress
| Branding form to FiServ | Provide input for form | In Progress |  |  | 2016-04-29
| Customer communications/alerts | Discuss needs with COPs | In Progress
| Domain | Need to define | In Progress
| Analytics | Need to define | In Progress
Tracking & Reporting
| Alight audit recommendations |  | Complete
| Solution for launch |  | Complete | 2016-03-31
| Define business requirements | Need to define | In Progress
| TCI/Alight solutions discussion | Need to define | In Progress
| Review site in staging enviroment to set up tracking | TCI to provide access to Alight | In Progress
| TCI integration | Channel mix ID cookie | In Progress
|  | GTM containers | In Progress
|  | Form code in URL | In Progress
|  | Has Offers postback | In Progress
|  | Application funnel | In Progress
|  | Current vs. new URL logic [redirects] | In Progress
|  | Ops/LPO LOS user ID | In Progress
|  | Campign information storage | In Progress
|  | Tracking conversion system | In Progress
| Marketing acquisition reporting | Need to define | In Progress
Marketing Site Updates (Sitecore)
| Changes to current Marketing Sitecore site to align with new application features | Audit Sitecore site | In Progress
| Sitecore welcome page (custom content per applicant decisions) |  | Complete