## Mkt Tasks
| Go-Live Date | OMEGA - MARKETING TASKS
Task Ref # | Cutover/Post-Go-Live | Category | Task ID | Task | Responsible Business Unit | Business Owner | Target Start Date (T minus Go-Live) | Content Draft | Final To Compliance | Compliance Approval | Release For Production | Deploy to Test | Marketing Sign Off | Deploy Live Date/Time | Take Down Date/Time | Current Status | Task Description
|  | Paymentus | 1 | UI stylesheets/specifications |  |  |  | NA | NA | NA | 9.11.17 | 1.8.18 | 1.8.18 | 1.22.17 | NA | Waiting to deploy live | Design specifications
|  | Paymentus | 2 | Supply PS logo file |  |  |  | NA | NA | NA | 9.11.17 | 11.14.17 | 12.13.17 | 1.22.17 | NA | Waiting to deploy live | Logo file
|  | Paymentus | 3 | Supply PS logo link |  |  |  | NA | NA | NA | 9.11.17 | 11.14.17 | 12.13.17 | 1.22.17 | NA | Waiting to deploy live | PS Logo Link: PioneerMilitaryLoans.com
|  | Paymentus | 4 | Login page edits |  |  |  | 10.5.17 | 10.6.17 | 10.10.17 | 10.5.17 | 11.14.17 | 1.5.18 | 1.22.17 | NA | Waiting to deploy live | Content edits.
|  | Paymentus | 5 | Accounts page intro content edits |  |  |  | 10.5.17 | 10.6.17 | 10.10.17 | 10.5.17 | 11.14.17 | 12.13.17 | 1.22.17 | NA | Waiting to deploy live
|  | Paymentus | 6 | Email subject line/intro paragraph for confirmation emails |  |  |  | 9.5.17 | 9.21.17 | 9.28.18 | 9.11.17 | 11.14.17 | 12.13.17 | 1.22.17 | NA | Waiting to deploy live | Content edits.
|  | Paymentus | 7 | "From" Email Address/From Name |  |  |  | NA | NA | NA | 9.11.17 | 11.14.17 | 12.13.17 | 1.22.17 | NA | Waiting to deploy live | From Name: Pioneer Services From Email Address: payments@pioneerservices.com
|  | Paymentus | 8 | Custom Emails |  |  |  | NA | NA | NA | NA | 11.14.17 | 12.13.17 | 1.22.17 | NA | Waiting to deploy live
|  | ROL | 9 | Log In page - revise intro copy |  |  |  | 9.11.17 | 9.21.17 | 9.28.17 | 9.14.17 | 1.8.18 | 1.8.18 | 1.22.17 | NA | Waiting to deploy live
|  | ROL | 10 | Enroll page - revise intro copy |  |  |  | 9.11.17 | 9.21.17 | 9.28.17 | 9.14.17 | 10.3.17 | 10.4.17 | 1.22.17 | NA | Waiting to deploy live
|  | ROL | 11 | Change 'Allotment Setup' to 'Pay By Allotment' in footer |  |  |  | 9.11.17 | NA | NA | 9.14.17 | 10.3.17 | 10.4.17 | 1.22.17 | NA | Waiting to deploy live
|  | ROL | 12 | Updated URLs for: Footer links Payments and Apply Now tabs in nav bar |  |  |  | 9.11.17 | NA | NA | 9.14.17 | 10.3.17 | 10.4.17 | 1.22.17 | NA | Waiting to deploy live
|  | ROL | 13 | Production url for Payments link (PSPY) |  |  |  | NA | NA | NA | 9.26.17 | 10.3.17 | 10.4.17 | 1.22.17 | NA | Waiting to deploy live
|  | ROL | 14 | Custom emails |  |  |  | 4.14.16 | 4.20.16 | 4.26.16 | 5.4.16 | 10.3.17 | 10.4.17 | 1.22.17 | NA | Waiting to deploy live
|  | TMS | 15 | Funding (EFT) |  |  |  | 10.4.17 | 10.6.17 | 10.10.17 | 10.5.17 | 10.24.17 | 11.15.17 | 1.22.17 | NA | Waiting to deploy live | Content/link edits
|  | TMS | 16 | Funding (Physical Disbursement) |  |  |  | 10.4.17 | 10.6.17 | 10.10.17 | 10.5.17 | 10.24.17 | 11.15.17 | 1.22.17 | NA | Waiting to deploy live | Content/link edits
|  | TMS | 17 | Partial Application |  |  |  | 9.12.17 | 9.21.17 | 9.28.17 | 9.15.17 | 10.24.17 | 11.15.17 | 1.22.17 | NA | Waiting to deploy live | Content edits
|  | Communications Engine | 18 | New Welcome Email |  |  |  | 10.5.17 | 10.6.17 | 10.10.17 | 10.11.12 | 10.12.17 | 10.13.17 | 1.22.17 | NA | Waiting to deploy live | Content creation
|  | Communications Engine | 19 | Account Management Triggered Emails UI |  |  |  | Complete | Complete | Complete | Complete | Complete | 10.13.17 | 1.22.17 | NA | Waiting to deploy live | Content edits
|  | Communications Engine | 20 | Collections Triggered Emails UI |  |  |  | 10.30.17 | 11.1.17 | 11.3.17 | 11.6.17 | 11.8.17 | 11.14.17 | 1.22.17 | NA |  | Content edits
|  | Communications Engine | 21 | Review of variable data content formatting |  |  |  | NA | NA | NA | NA | 12.12.17 | 12.22.18 | 1.22.17 | NA | Waiting to test
|  | secure.pml.com | 22 | Transaction Site (secure.pml.com) "site down" messaging |  |  |  | 9.28.17 | 10.4.17 | 10.9.17 | 10.27.17 | 1.11.17 | 1.15.18 | 1.18.18 | 1.22.18 | Deployed | Updated content with new lauch date sent to IT 10.27.17 Site down messaging will display on the application site (secure.PML.com) in alignment with the system takedown. Marketing will create content. IT will manage deploy.
|  | secure.pml.com | 23 | Login Screen Content Edits |  |  |  | 9.12.17 | 9.21.17 | 9.28.17 | 9.15.17 | 9.27.19 | 10.3.17 | 1.22.18 | NA | Waiting to deploy live | Content edits to return to application login screen
|  | secure.pml.com | 24 | Log In Error Message (No Active App Found) |  |  |  | 9.12.17 | 9.21.17 | 9.28.17 | 9.15.17 | 11.7.17 | 11.15.17 | 1.22.18 | NA | Waiting to deploy live | No current active application can be found in the system
|  | secure.pml.com | 25 | Remove Login link in utility navigation |  |  |  | NA | NA | NA | 9.15.17 | 9.27.19 | 10.3.17 | 1.22.18 | NA | Waiting to deploy live
|  | secure.pml.com | 26 | Application Page 2 Edits (setting up UN/PW) |  |  |  | 9.12.17 | 9.21.17 | 9.28.17 | 9.15.17 | 9.27.19 | 10.3.17 | 1.22.18 | NA | Waiting to deploy live | Edits to on-screen and popup text.
|  | Sitecore |  | Sitecore Content Freeze Start |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | 1.16.18
|  | Sitecore | 27 | Pre-Launch Home Page Hero - Desktop | Marketing | Randy Freese | Week of 4.10.17 | 9.28.17 | 10.4.17 | 10.9.17 | NA | 1.12.18 | 1.12.18 | 1.15.18 | 1.18.18 | Deployed | Alert website visitors to upcoming system changes/downtime: linking to Per-Launch System Upgrade page
|  | Sitecore | 28 | Pre-Launch Home Page Banner - Mobile |  |  |  | 9.28.17 | 10.4.17 | 10.9.17 | NA | 1.12.18 | 1.12.18 | 1.15.18 | 1.18.18 | Deployed | Alert website visitors to upcoming system changes/downtime: linking to Per-Launch System Upgrade page
|  | Sitecore | 29 | Pre-Launch Right Rail (Desktop/Mobile/Landing) [Home/Contact Us/Locations Home/About Us/FAQs] |  |  |  | 9.28.17 | 10.4.17 | 10.9.17 | NA | 1.12.18 | 1.12.18 | 1.15.18 | 1.18.18 | Deployed | Alert website visitors to upcoming system changes/downtime: linking to Per-Launch System Upgrade page
|  | Sitecore | 30 | System Downtime Home Page Hero - Desktop |  |  |  | 9.28.17 | 10.4.17 | 10.9.17 | NA | 1.16.18 | 1.17.18 | 1.18.18 | 1.22.18 | Deployed | Alert website visitors of current unavailable services: linking to Downtime System Upgrade page. Messaging removed upon launch of all systems.
|  | Sitecore | 31 | System Downtime Home Page Banner - Mobile |  |  |  | 9.28.17 | 10.4.17 | 10.9.17 | NA | 1.16.18 | 1.17.18 | 1.18.18 | 1.22.18 | Deployed | Alert website visitors of current unavailable services: linking to Downtime System Upgrade page. Messaging removed upon launch of all systems.
|  |  | 32 | System Downtime Homepage Right Rail (Desktop/Mobile) [Home/Contact Us/Locations Home/About Us/FAQs] | [7 empty] | 1.16.18 | 1.17.18 | 1.18.18 | 1.22.18 | Deployed
|  | Sitecore | 33 | New Page: Pre-launch system enhancements |  |  |  | 9.28.17 | 10.4.17 | 10.9.17 | NA | 1.12.18 | 1.12.18 | 1.12.18 | 1.18.18 | Deployed | Provides more info on upcoming system changes
|  | Sitecore | 34 | New Page: Downtime system enhancements |  |  |  | 9.28.17 | 10.25.17 | 11.1.17 | NA | 1.16.18 | 1.17.18 | 1.18.18 | 1.22.18 | Deployed | Provides more info on upcoming system changes. Includes short form to collect customer info to notify when system back up (TBD).
|  | Sitecore | 35 | New Page: Login Page |  |  |  | 10.3.17 | 11.7.17 | 11.10.17 | NA | 1.16.18 | 1.18.18 | 1.22.18 | NA | Waiting to deploy live | New page to direct applicants/customers to the right platform matching their intent.
|  | Sitecore | 36 | FAQs: review/update as needed |  |  |  | 10.3.17 | 10.9.17 | 10.10.17 | NA | 1.16.18 | 1.18.18 | 1.22.18 | NA | Waiting to deploy live | Update content.
|  | Sitecore | 37 | Military Allotment: review/update as needed |  |  |  | 10.3.17 | 10.4.17 | 10.9.17 | NA | 1.16.18 | 1.18.18 | 1.22.18 | NA | Waiting to deploy live | Update content.
|  | Sitecore | 38 | New Page: Allotment Authorization | 10.3.17 | 10.4.17 | 10.10.17 | 10.3.17 | 10.4.17 | 10.9.17 | NA | 1.16.18 | 1.18.18 | 1.22.18 | NA | Waiting to deploy live
|  | Sitecore | 39 | Contact Us: review/update as needed |  |  |  | 10.3.17 | 10.4.17 | 10.9.17 | NA | 1.16.18 | 1.18.18 | 1.22.18 | NA | Waiting to deploy live | Update content.
|  | Sitecore | 40 | Online Account Access: review/update as needed |  |  |  | 10.3.17 | 10.4.17 | 10.9.17 | NA | 1.16.18 | 1.18.18 | 1.22.18 | NA | Waiting to deploy live | Update content.
|  | Sitecore | 41 | Welcome Page: review/update as needed |  |  |  | 10.3.17 | 10.4.17 | 10.9.17 | NA | 1.16.18 | 1.18.18 | 1.22.18 | NA | Waiting to deploy live | Update content.
|  | Sitecore | 42 | Application Status Right Rail |  |  |  | 10.3.17 | 10.4.17 | 10.9.17 | NA | 1.16.18 | 1.18.18 | 1.22.18 | NA | Waiting to deploy live | Update content.
|  | Sitecore | 43 | FAQ Page/Local App Pages: Left Nav MyAccount/Utility Nav |  |  |  | 10.3.17 | 10.4.17 | 10.9.17 | NA | 1.16.18 | 1.18.18 | 1.22.18 | NA | Waiting to deploy live | Update content.
|  | Sitecore | 44 | Post App Redirect: review/update as needed |  |  |  | 10.3.17 | 10.4.17 | 10.9.17 | NA | 1.16.18 | 1.18.18 | 1.22.18 | NA | Waiting to deploy live | Update content.
|  | Sitecore | 45 | MyAccount & Log In Links/Buttons: update redirects |  |  |  | 10.3.17 | NA | NA | NA | 1.16.18 | 1.18.18 | 1.22.18 | NA | Waiting to deploy to test | Update links
|  | Sitecore | 46 | Deploy Revised Sitecore Apply/Login Modules - Home Page Right Rail (Desktop/Mobile) |  |  |  | Complete | Complete | Complete | Complete | 1.12.18 | TBD | 1.22.18 | NA | Waiting to deploy live | Updated homepage and right rail modules (new design, content, functionality)
|  | Sitecore | 47 | Native Mobile App Sitecore Page Updates | Marketing | Randy Freese | 4.24.17 | 10.3.17 | 10.4.17 | 10.9.17 | NA | 1.16.18 | 1.18.18 | 1.22.18 | NA | In conjunction with DT/Mobile | Update content/links.
|  | Customer Communications | 48 | System Downtime/Upgrade Talking Points for COPS/LPOs |  |  |  | 10.27.18 | NA | NA | NA | NA | NA | NA | NA | Complete | Final talking points delivered by 10.12 so ready for questions on 10.16.
|  | Customer Communications | 49 | ROL/Paymentus Training Instructions for COPS/LPOs |  |  |  | 12.13.17 | NA | NA | NA | NA | NA | NA | NA | Complete | Ready for COPs/LPOs to use
|  | Customer Communications | 50 | Email List Development Process |  |  |  | NA | NA | NA | NA | NA | NA | 1.12.18 | NA | Reporting to provide lists | List (new creation process) complete and ready for new lists downloads by 10.25.
|  | Customer Communications | 51 | Customer Pre-Launch Alert Email Send 1 |  |  |  | 10.9.17 | 10.26.17 | 11.2.17 | NA | 1.12.18 | 1.12.18 | 1.12.18 | NA | Complete | Email all active customers (Present Borrowers) announcing upcoming system downtime (info on services being impacted).
|  | Customer Communications | 52 | Customer Pre-Launch Alert Email Send 2 |  |  |  |  | NA | NA | NA | 1.16.18 | 1.16.18 | 1.16.18 | NA | Complete | Same as above
|  | Customer Communications | 53 | Customer Post-Launch Emails |  |  |  | 10.9.17 | 10.26.17 | 11.2.17 | NA | 1.23.18 | 1.23.18 | 1.23.18 | NA | Waiting to deploy to test | Email all active customers (Present Borrowers) to announce system enhancements and changes in their login credentials.
|  | Customer Communications | 54 | Active Applicant Pre-Launch Alert Email Send 1 |  |  |  | 10.9.17 | 10.25.17 | 11.1.17 | NA | 1.15.17 | 1.15.17 | 1.15.17 | NA | Complete | Email all applicants in the AM with an active application to encourage completion/booking by midnight on 1.17. Alert applicants that applications not booked are still valid but will not be processed until 1.22..18 (when system goes live).
|  |  |  | Active Applicant Pre-Launch Alert Email Send 2 |  |  |  | 10.9.17 | NA | NA | NA | 1.17.18 | 1.17.18 | 1.17.18 |  | Complete | Same as above in the AM with addition of active apps since send on 1/15.
|  | Customer Communications | 55 | Active Applicant Post-Launch Email |  |  |  | 10.9.17 | 10.25.17 | 11.1.17 | NA | 1.23.18 | 1.23.18 | 1.23.18 | NA | Waiting to deploy to test | Email all applicants with an open/active application to alert them that they can log in to check the status of their application and complete the process.
|  | Customer Communications | 56 | Downtime Form Collect Outbound Communication Email |  | Open | 10.26.17? | 10.9.17 | 10.26.17 | 11.2.17 | NA | 1.23.18 | 1.23.18 | 1.23.18 | NA | Waiting to deploy to test | Alert site visitors who requested to be alerted when site is back up.
|  | Customer Communications | 57 | IVR Messaging During System Down Time |  |  |  | 10.10.17 | 10.25.17 | 11.1.17 | NA | NA | NA | 1.18.18 | 1.22.17 | Message recorded - Waiting to deploy live | The IVR message has to be changed in conjucntion with when the system goes down but can be pre-recorded Determine IVR system capabilities during cutover for pre-launch/during downtime for messaging purposes
|  | Customer Communications | 58 | IVR Messaging Post Launch |  |  |  | NA | NA | NA | NA | NA | NA | 1.22.18 | NA | Reset to original messaging | Restore IVR messaging back to originat state
|  | Lead Source | 59 | Pause Customer Email Solicitations (ITAs, etc.) |  |  |  | NA | NA | NA | NA | NA | NA | 1.18.18 | 1.24.18 | Dates indicate stop/resume | Pause pre application take down. Restart post all systems up.
#REF! | Cutover | Lead Source | 60 | Pause Paid Search Campaigns | Marketing | Randy Freese |  | NA | NA | NA | NA | NA | NA | 1.18.18 | 1.23.18 | Dates indicate stop/resume | Pause in alignment with application take down. Restart with app launch.
#REF! | Cutover | Lead Source | 62 | Pause Online Display Ads | Marketing | Randy Freese |  | NA | NA | NA | NA | NA | NA | 1.18.18 | 1.23.18 | Dates indicate stop/resume | Pause in alignment with application take down. Restart with app launch.
#REF! | Cutover | Lead Source | 61 | Affiliate Notification Email Pre Launch | Marketing | Randy Freese |  | 10.9.17 | 10.25.17 | 11.1.17 | NA | NA | NA | 1.12.18 | NA | Complete | Email affiliate partners to notify of system down time. To be sent via Outlook.
|  | Lead Source | 63 | Affiliate Notification Email Post Launch |  |  |  | 10.5.17 | 10.25.17 | 11.1.17 | NA | NA | NA | 1.23.18 | NA | Waiting to send | Email affiliate partners to notify of system up. To be sent via Outlook.
#REF! | Cutover |  |  |  | Marketing | Randy Freese
|  | Mobile Application | 64 | Native App Banner Pre-Launch |  |  |  | 9.28.17 | 10.4.17 | 10.9.17 | NA | 1.12.18 | 1.12.18 | 1.15.18 | 1.17.18 | Can review in Buildfire prior to pushing live | Potential updates needed to content and or links. Updates made via mobile app platform.
|  | Mobile Application | 65 | Native App Banner Downtime |  |  |  | 9.28.17 | 10.4.17 | 10.9.17 | NA | 1.17.18 | 1.17.18 | 1.18.18 | 1.22.18 | Can review in Buildfire prior to pushing live
|  | SOPs | 66 | Marketing Project Management |  |  |  | 10.27.17 | 11.14.17 | 11.17.17 | NA | NA | NA | 1.24.18 | NA
|  | SOPs | 67 | Website Change Management |  |  |  | 10.27.17 | 11.14.17 | 11.17.17 | NA | NA | NA | 1.24.18 | NA

## Sys Conv Comm Tasks
System Conversion Communication Timelines | Jan 12 (Fri) | Jan 13 (Sat) | Jan 14 (Sun) | Jan 15 (Mon) | Jan 16 (Tue) | Jan 17 (Wed) | Jan 18 (Thu) | Jan 19 (Fri) | Jan 20 (Sat) | Jan 21 (Sun) | Jan 22 (Mon) | Jan 23 (Tue) | Jan 24 (Wed) | Jan 25 (Thu)
Customer Interface/Marketing Campaign Up-Time/Down-Time
Customer Access to Transaction Systems (Application/MyAccount/IVR) Systems go down starting 11:00 PM CT on 1.17 and new systems (Omega, ROL, Paymentus) go live around 12:00 noon CT on 1.22. | < | [12 empty] | >
Brand Website (PML.com/Sitecore) Website does not go down. Information updates and UI to provide access to new platforms (Omega, ROL, Paymentus) goes live in alignment with system launch on 1.22. | < | [12 empty] | >
Search Campaigns (paused during system conversion--10 PM 1.17) Un-pause post launch 1.22/23 (pending) | < | [12 empty] | >
Online Display Campaigns (paused during system conversion--10 PM 1.17) Un-pause post launch 1.23 | < | [12 empty] | >
Affiliate Referrals (paused during system conversion 10 PM 1.17) | < | [12 empty] | >
ITA Email Campaigns (paused pre/during/post system conversion) | < | [12 empty] | >
Customer/Partner Communications
System Conversion Talking Points (COPs/LPOs) | [13 empty] | >
Customer Pre/Post Conversion Alert Emails | Pre |  |  |  | Pre | [6 empty] | Post |  | Post
Active Applicant Pre/Post Conversion Alert Emails |  |  |  | Pre | Pre | Pre | [5 empty] | Post |  | Post
Post Conversion Email to Website Visitors (collected during down system) | [11 empty] | Post
Affiliate Notification Pre/Post Conversion Alert Emails/Phone Calls | Pre |  |  | Pre | Pre | [6 empty] | Post
Brand Website Pre Conversion Messaging (Hero/Banners/Info Pages)
Native Mobile App Pre Conversion Messaging (Banner)
Brand Website System Downtime Messaging (Hero/Banners/Info Pages)
Native Mobile App System Downtime Messaging (Banner)
Secure Site (Application/Login) System Downtime Messaging
IVR System Downtime Message
Brand Website Post Conversion Messaging (Page Content/Transaction Links) | [13 empty] | >
Origination Follow-Up Communications (TMS). Edits go live with system launch. | < | [12 empty] | >
Account Service/Collections Follow-Up Communications. Switch from TMS to new COMM Engine at system launch. | < | [12 empty] | >
Other Important Timelines/Marketing Related Tasks:
Pamentus UI In Production (Live ROL provides only customer access) Paymentus UI available for review/testing on 1.18. Sign off prior to EOD 1.19 | [12 empty] | >
Fiserv ROL UI In Production (Customer ROL access only through Sitecore) ROL available for UI review/testing 8 AM CT 1.21. Sign off prior to noon 1.21. | [12 empty] | >
Secure Site (internal access 1 AM on 1.22). Push to Production after all internal sign offs and in alignment with Sitecore Post Launch Messaging around noon on 1.22 | [12 empty] | >
Communication Engine Post-Launch Validation | [12 empty] | >