## Sheet1
ID | LATE | Task Name | Duration | Predecessors | % Complete | Start | Finish | Resource Names | Issue | Comments
367 | No | Consumer Portal | 113.4 days |  | 72% | 2018-04-19 | 2018-09-27
368 | No | Speed and Responsiveness Testing | 90 days |  | 52% | 2018-04-19 | 2018-08-23
369 | No | In Client Testing | 3 days |  | 100% | 2018-07-25 | 2018-07-27
370 | No | Application Testing | 3 days |  | 100% | 2018-07-25 | 2018-07-27 | Mktg
371 | No | Speed Results Captured and Communicated | 1 day | 370FF | 100% | 2018-07-27 | 2018-07-27 | TCI
372 | No | Constraints Identified | 1 day |  | 100% | 2018-04-19 | 2018-04-19 | TCI
373 | No | Content Updates Identified | 10 days | 371 | 100% | 2018-07-30 | 2018-08-10 | Mktg
374 | Yes | Issue Resolution | 7 days | 373 | 0% | 2018-08-13 | 2018-08-21 | TCI
375 | Yes | Compliance Content Signoff | 5 days | 373 | 0% | 2018-08-13 | 2018-08-17 | Mktg
376 | Yes | Content Updates Completed | 2 days | 374 | 0% | 2018-08-22 | 2018-08-23 | TCI
377 | Yes | RTA/Reset Security Code | 59 days |  | 27% | 2018-05-07 | 2018-07-27
378 | No | Development | 0 days |  | 100% | 2018-05-07 | 2018-05-07
382 | No | In Client Testing | 4 days |  | 100% | 2018-05-07 | 2018-05-10
383 | No | Content | 4 days | 379 | 100% | 2018-05-07 | 2018-05-10 | Mktg
384 | No | Design | 4 days | 379 | 100% | 2018-05-07 | 2018-05-10 | Mktg
385 | No | Functionality | 4 days | 379 | 100% | 2018-05-07 | 2018-05-10 | Mktg
386 | Yes | Issue Resolution | 56 days | 382SS+1 day | 13% | 2018-05-08 | 2018-07-25 | TCI |  | Open app redirect currently turned off - Need to schedule controlled test with TCI
387 | Yes | User Acceptance Testing Passed | 2 days | 386 | 0% | 2018-07-26 | 2018-07-27 | Mktg
388 | Yes | Business Owner Signoff | 0 days | 387 | 0% | 2018-07-27 | 2018-07-27 | Mktg
389 | No | Utility Pages | 55 days |  | 98% | 2018-05-09 | 2018-07-25
390 | No | Legal Pages | 10 days |  | 100% | 2018-05-09 | 2018-05-22
391 | No | Development | 0 days |  | 100% | 2018-05-09 | 2018-05-09 | TCI
395 | No | In Client Testing | 5 days |  | 100% | 2018-05-09 | 2018-05-15 | Mktg
399 | No | Issue Resolution | 7 days | 395SS+1 day | 100% | 2018-05-10 | 2018-05-18 | Mktg
400 | No | User Acceptance Testing Passed | 2 days | 399 | 100% | 2018-05-21 | 2018-05-22 | Mktg
401 | No | Business Owner Signoff | 0 days | 400 | 100% | 2018-05-22 | 2018-05-22
402 | No | Contact Us | 8 days |  | 100% | 2018-05-09 | 2018-05-18
403 | No | Development | 0 days |  | 100% | 2018-05-09 | 2018-05-09 | TCI
407 | No | In Client Testing | 5 days |  | 100% | 2018-05-09 | 2018-05-15 | Mktg
411 | No | Issue Resolution | 7 days | 407SS+1 day | 100% | 2018-05-10 | 2018-05-18 | Mktg
412 | No | User Acceptance Testing Passed | 2 days | 407 | 100% | 2018-05-16 | 2018-05-17 | Mktg
413 | No | Business Owner Signoff | 0 days | 412 | 100% | 2018-05-17 | 2018-05-17
414 | No | FAQs | 8 days |  | 100% | 2018-05-09 | 2018-05-18
415 | No | Development | 0 days |  | 100% | 2018-05-09 | 2018-05-09 | TCI
419 | No | In Client Testing | 5 days |  | 100% | 2018-05-09 | 2018-05-15 | Mktg
423 | No | Issue Resolution | 7 days | 419SS+1 day | 100% | 2018-05-10 | 2018-05-18 | Mktg
424 | No | User Acceptance Testing Passed | 2 days | 419 | 100% | 2018-05-16 | 2018-05-17 | Mktg
425 | No | Business Owner Signoff | 0 days | 424 | 100% | 2018-05-17 | 2018-05-17
426 | No | Locations | 55 days |  | 92% | 2018-05-09 | 2018-07-25
427 | No | Development | 0 days |  | 100% | 2018-05-09 | 2018-05-09
431 | No | In Client Testing | 5 days |  | 100% | 2018-05-09 | 2018-05-15
435 | No | Issue Resolution | 7 days | 431SS+1 day | 100% | 2018-07-17 | 2018-07-25 | TCI
436 | Yes | User Acceptance Testing Passed | 2 days | 431 | 0% | 2018-05-16 | 2018-05-17 | Mktg
437 | Yes | Business Owner Signoff | 0 days | 436 | 0% | 2018-05-17 | 2018-05-17 | Mktg
438 | No | Application Page 1/Application Stop Page | 8 days |  | 50% | 2018-05-16 | 2018-05-25
439 | No | Development | 0 days |  | 100% | 2018-05-16 | 2018-05-16
443 | No | In Client Testing | 3 days |  | 100% | 2018-05-16 | 2018-05-18
444 | No | Content | 3 days | 431 | 100% | 2018-05-16 | 2018-05-18 | Mktg
445 | No | Design | 3 days | 431 | 100% | 2018-05-16 | 2018-05-18 | Mktg
446 | No | Functionality | 3 days | 431 | 100% | 2018-05-16 | 2018-05-18 | Mktg
447 | Yes | Issue Resolution | 7 days | 443SS+1 day | 0% | 2018-05-17 | 2018-05-25 | TCI
448 | Yes | User Acceptance Testing Passed | 2 days | 443 | 0% | 2018-05-21 | 2018-05-22 | Mktg |  | Open app redirect; data mismatch; 90-day since denied app rules currently turned off - Need to schedule controlled test with TCI
449 | Yes | Business Owner Signoff | 0 days | 448 | 0% | 2018-05-22 | 2018-05-22 | Mktg
450 | No | Application Page 2 | 8 days |  | 63% | 2018-05-17 | 2018-05-28 |  | 2725,2623, 2750 | 2621
451 | No | Development | 0 days |  | 100% | 2018-05-17 | 2018-05-17
455 | No | In Client Testing | 5 days |  | 100% | 2018-05-17 | 2018-05-23
456 | No | Content | 5 days | 443SS+1 day | 100% | 2018-05-17 | 2018-05-23 | Mktg
457 | No | Design | 5 days | 443SS+1 day | 100% | 2018-05-17 | 2018-05-23 | Mktg
458 | No | Functionality | 5 days | 443SS+1 day | 100% | 2018-05-17 | 2018-05-23 | Mktg
459 | Yes | Issue Resolution | 7 days | 455SS+1 day | 0% | 2018-05-18 | 2018-05-28 | TCI
460 | Yes | User Acceptance Testing Passed | 2 days | 455 | 0% | 2018-05-24 | 2018-05-25 | Mktg
461 | Yes | Business Owner Signoff | 0 days | 455 | 0% | 2018-05-23 | 2018-05-23 | Mktg
462 | No | Decision Waiting/Confirm Identity Page | 47 days |  | 89% | 2018-05-21 | 2018-07-25
463 | No | Development | 0 days |  | 100% | 2018-05-21 | 2018-05-21
467 | No | In Client Testing | 3 days |  | 100% | 2018-05-21 | 2018-05-23
468 | No | Content | 3 days | 455SS+2 days | 100% | 2018-05-21 | 2018-05-23 | Mktg
469 | No | Design | 3 days | 455SS+2 days | 100% | 2018-05-21 | 2018-05-23 | Mktg
470 | No | Functionality | 3 days | 455SS+2 days | 100% | 2018-05-21 | 2018-05-23 | Mktg
471 | No | Issue Resolution | 7 days | 468SS+1 day | 100% | 2018-07-17 | 2018-07-25 | TCI
472 | Yes | User Acceptance Testing Passed | 2 days | 467 | 0% | 2018-05-24 | 2018-05-25 | Mktg |  | Redirect to No Decision - need TCI to define max time before app is put into manual review
473 | Yes | Business Owner Signoff | 0 days | 472 | 0% | 2018-05-25 | 2018-05-25 | Mktg
474 | No | Application Denial | 8 days |  | 100% | 2018-05-24 | 2018-06-04
475 | No | Development | 0 days |  | 100% | 2018-05-24 | 2018-05-24
479 | No | In Client Testing | 4 days |  | 100% | 2018-05-24 | 2018-05-29
480 | No | Content | 4 days | 467 | 100% | 2018-05-24 | 2018-05-29 | Mktg
481 | No | Design | 4 days | 467 | 100% | 2018-05-24 | 2018-05-29 | Mktg
482 | No | Functionality | 4 days | 467 | 100% | 2018-05-24 | 2018-05-29 | Mktg
483 | No | Issue Resolution | 7 days | 479SS+1 day | 100% | 2018-05-25 | 2018-06-04 | TCI
484 | No | User Acceptance Testing Passed | 2 days | 479 | 100% | 2018-05-30 | 2018-05-31 | Mktg
485 | No | Business Owner Signoff | 0 days | 484 | 100% | 2018-05-31 | 2018-05-31 | Mktg
486 | No | Upload Docs/Confirm Upload | 8 days |  | 63% | 2018-05-30 | 2018-06-08 |  | 2593, 2594,2595, 2697 | Previous 2634, 2635
487 | No | Development | 0 days |  | 100% | 2018-05-30 | 2018-05-30
491 | No | In Client Testing | 5 days |  | 100% | 2018-05-30 | 2018-06-05
492 | No | Content | 5 days | 479 | 100% | 2018-05-30 | 2018-06-05 | Mktg
493 | No | Design | 5 days | 479 | 100% | 2018-05-30 | 2018-06-05 | Mktg
494 | No | Functionality | 5 days | 479 | 100% | 2018-05-30 | 2018-06-05 | Mktg
495 | Yes | Issue Resolution | 7 days | 491SS+1 day | 0% | 2018-05-31 | 2018-06-08 | TCI
496 | Yes | User Acceptance Testing Passed | 2 days | 491 | 0% | 2018-06-06 | 2018-06-07 | Mktg
497 | Yes | Business Owner Signoff | 0 days | 496 | 0% | 2018-06-07 | 2018-06-07 | Mktg
498 | No | Loan Offers/Ancillary Products | 9 days |  | 85% | 2018-06-06 | 2018-06-18 |  |  | 50% is just for Auto Protect
499 | No | Development | 0 days |  | 100% | 2018-06-06 | 2018-06-06
503 | No | In Client Testing | 7 days |  | 100% | 2018-06-06 | 2018-06-14
504 | No | Content | 7 days | 491 | 100% | 2018-06-06 | 2018-06-14 | Mktg
505 | No | Design | 7 days | 491 | 100% | 2018-06-06 | 2018-06-14 | Mktg
506 | No | Functionality | 7 days | 491 | 100% | 2018-06-06 | 2018-06-14 | Mktg
507 | No | Issue Resolution | 7 days | 503SS+1 day | 50% | 2018-06-07 | 2018-06-15 | TCI
508 | No | User Acceptance Testing Passed | 2 days | 503 | 50% | 2018-06-15 | 2018-06-18 | Mktg
509 | No | Business Owner Signoff | 0 days | 508 | 50% | 2018-06-18 | 2018-06-18 | Mktg |  | 1) Offers - need test data for Offer #6 scenario2) Product popup 1 & 2 - currently cannot review, need approval from biz owners to accept
510 | No | Loan Disbursement Page | 19 days |  | 65% | 2018-06-15 | 2018-07-12 |  | 2678 | Previous 2646,
511 | No | Development | 0 days |  | 100% | 2018-06-15 | 2018-06-15
515 | No | In Client Testing | 10 days |  | 100% | 2018-06-15 | 2018-06-28
516 | No | Content | 10 days | 503 | 100% | 2018-06-15 | 2018-06-28 | Mktg
517 | No | Design | 10 days | 503 | 100% | 2018-06-15 | 2018-06-28 | Mktg
518 | No | Functionality | 10 days | 503 | 100% | 2018-06-15 | 2018-06-28 | Mktg
519 | Yes | Issue Resolution | 7 days | 515SS+1 day | 0% | 2018-06-18 | 2018-06-26 | TCI
520 | Yes | User Acceptance Testing Passed | 2 days | 515 | 0% | 2018-06-29 | 2018-07-02 | Mktg
521 | Yes | Business Owner Signoff | 7 days | 520 | 0% | 2018-07-03 | 2018-07-12 | Mktg | 2671 | need test data for Loan Amount presentation #4; cannot currently simulate a pass on Express Deposit
522 | No | Loan Repayment Page | 12 days |  | 77% | 2018-06-22 | 2018-07-10 |  | ,2697,2693,,2722,,2750
523 | No | Development | 0 days |  | 100% | 2018-06-22 | 2018-06-22
527 | No | In Client Testing | 10 days |  | 100% | 2018-06-22 | 2018-07-06
528 | No | Content | 10 days | 515SS+5 days | 100% | 2018-06-22 | 2018-07-06 | Mktg
529 | No | Design | 10 days | 515SS+5 days | 100% | 2018-06-22 | 2018-07-06 | Mktg
530 | No | Functionality | 10 days | 515SS+5 days | 100% | 2018-06-22 | 2018-07-06 | Mktg
531 | Yes | Issue Resolution | 7 days | 527SS+1 day | 0% | 2018-06-25 | 2018-07-03 | TCI
532 | Yes | User Acceptance Testing Passed | 2 days | 527 | 0% | 2018-07-09 | 2018-07-10 | Mktg
533 | Yes | Business Owner Signoff | 0 days | 532 | 0% | 2018-07-10 | 2018-07-10 | Mktg
534 | No | Loan Summary/Locked Loan Summary | 49 days |  | 79% | 2018-06-29 | 2018-09-07 |  | 2715271426592750
535 | No | Development | 0 days |  | 100% | 2018-06-29 | 2018-06-29
539 | No | In Client Testing | 10 days |  | 100% | 2018-08-22 | 2018-09-05
540 | No | Content | 10 days | 528SS+5 days | 100% | 2018-08-22 | 2018-09-05 | Mktg
541 | No | Design | 10 days | 528SS+5 days | 100% | 2018-08-22 | 2018-09-05 | Mktg
542 | No | Functionality | 10 days | 528SS+5 days | 100% | 2018-08-22 | 2018-09-05 | Mktg
543 | No | Issue Resolution | 17 days | 539SS+1 day | 50% | 2018-07-02 | 2018-09-05 | TCI
544 | Yes | User Acceptance Testing Passed | 2 days | 539 | 0% | 2018-09-06 | 2018-09-07 | Mktg |  | need test data for Loan Amount presentation #4; cannot currently simulate a pass on Express Deposit
545 | Yes | Business Owner Signoff | 0 days | 544 | 0% | 2018-09-07 | 2018-09-07 | Mktg
546 | No | Doc Prep/EOrig | 53.4 days |  | 68% | 2018-07-13 | 2018-09-27 |  | 2739 | Previou 2674
547 | No | Development | 0 days |  | 100% | 2018-07-13 | 2018-07-13
551 | No | In Client Testing | 25.4 days |  | 100% | 2018-08-20 | 2018-09-25
552 | No | Content | 2 days | 539 | 100% | 2018-08-20 | 2018-09-07 | Mktg
553 | No | Design | 2 days | 539 | 100% | 2018-08-20 | 2018-09-07 | Mktg
554 | No | Functionality | 2 days | 539 | 100% | 2018-08-20 | 2018-09-07 | Mktg
555 | No | Cross Team Document Validation | 13.4 days | 539 | 100% | 2018-09-06 | 2018-09-25 |  |  | New Task Added 8/23
556 | Yes | Issue Resolution | 7 days | 551SS+1 day | 0% | 2018-08-21 | 2018-08-29 | TCI
557 | Yes | User Acceptance Testing Passed | 2 days | 551 | 0% | 2018-09-25 | 2018-09-27 | Mktg |  | retest Doc Prep once page transitions are implemented by TCI
558 | Yes | Business Owner Signoff | 0 days | 557 | 0% | 2018-09-27 | 2018-09-27 | Mktg
559 | No | Loan Recap Page | 33 days |  | 68% | 2018-07-16 | 2018-08-29
560 | No | Development | 0 days |  | 100% | 2018-07-16 | 2018-07-16
564 | No | In Client Testing | 5 days |  | 100% | 2018-08-21 | 2018-08-27
565 | No | Content | 5 days | 551SS+1 day | 100% | 2018-08-21 | 2018-08-27 | Mktg | 2671 | Resolved/passed/closed
566 | No | Design | 5 days | 551SS+1 day | 100% | 2018-08-21 | 2018-08-27 | Mktg
567 | No | Functionality | 5 days | 551SS+1 day | 100% | 2018-08-21 | 2018-08-27 | Mktg
568 | Yes | Issue Resolution | 5 days | 564SS+1 day | 0% | 2018-08-22 | 2018-08-28 | TCI
569 | Yes | User Acceptance Testing Passed | 2 days | 564 | 0% | 2018-08-28 | 2018-08-29 | Mktg
570 | Yes | Business Owner Signoff | 0 days | 569 | 0% | 2018-08-29 | 2018-08-29 | Mktg
571 | No | System Response Pages | 13 days |  | 57% | 2018-07-19 | 2018-08-06
572 | Yes | No Decision | 9 days |  | 40% | 2018-07-19 | 2018-07-31
573 | No | Development | 0 days |  | 100% | 2018-07-19 | 2018-07-19
577 | No | In Client Testing | 2 days |  | 100% | 2018-07-20 | 2018-07-23
578 | No | Content | 2 days | 564SS+3 days | 100% | 2018-07-20 | 2018-07-23 | Mktg
579 | No | Design | 2 days | 564SS+3 days | 100% | 2018-07-20 | 2018-07-23 | Mktg
580 | No | Functionality | 2 days | 564SS+3 days | 100% | 2018-07-20 | 2018-07-23 | Mktg
581 | Yes | Issue Resolution | 7 days | 577SS+1 day | 0% | 2018-07-23 | 2018-07-31 | TCI
582 | Yes | User Acceptance Testing Passed | 2 days | 577 | 0% | 2018-07-24 | 2018-07-25 | Mktg
583 | Yes | Business Owner Signoff | 0 days | 582 | 0% | 2018-07-25 | 2018-07-25 | Mktg
584 | No | No Response (Tech Difficulties) | 13 days |  | 77% | 2018-07-19 | 2018-08-06 |  | 2741,2742, | Need to Schedule Downtime
585 | No | Development | 0 days |  | 100% | 2018-07-19 | 2018-07-19
589 | No | In Client Testing | 10 days |  | 100% | 2018-07-20 | 2018-08-02
590 | No | Content | 10 days | 578SS | 100% | 2018-07-20 | 2018-08-02 | Mktg
591 | No | Design | 10 days | 578SS | 100% | 2018-07-20 | 2018-08-02 | Mktg
592 | No | Functionality | 10 days | 578SS | 100% | 2018-07-20 | 2018-08-02 | Mktg
593 | Yes | Issue Resolution | 7 days | 589SS+1 day | 0% | 2018-07-23 | 2018-07-31 | TCI
594 | Yes | User Acceptance Testing Passed | 2 days | 589 | 0% | 2018-08-03 | 2018-08-06 | Mktg
595 | Yes | Business Owner Signoff | 0 days | 594 | 0% | 2018-08-06 | 2018-08-06 | Mktg
596 | Yes | Session Ended | 9 days |  | 40% | 2018-07-19 | 2018-07-31 |  | 273727382740
597 | No | Development | 0 days |  | 100% | 2018-07-19 | 2018-07-19
601 | No | In Client Testing | 2 days |  | 100% | 2018-07-20 | 2018-07-23
602 | No | Content | 2 days | 578SS | 100% | 2018-07-20 | 2018-07-23 | Mktg
603 | No | Design | 2 days | 578SS | 100% | 2018-07-20 | 2018-07-23 | Mktg
604 | No | Functionality | 2 days | 578SS | 100% | 2018-07-20 | 2018-07-23 | Mktg
605 | Yes | Issue Resolution | 7 days | 601SS+1 day | 0% | 2018-07-23 | 2018-07-31 | TCI
606 | Yes | User Acceptance Testing Passed | 2 days | 601 | 0% | 2018-07-24 | 2018-07-25 | Mktg
607 | Yes | Business Owner Signoff | 0 days | 606 | 0% | 2018-07-25 | 2018-07-25 | Mktg
608 | Yes | Log Off Page | 9 days |  | 40% | 2018-07-19 | 2018-07-31 |  | 27322734
609 | No | Development | 0 days |  | 100% | 2018-07-19 | 2018-07-19
613 | No | In Client Testing | 2 days |  | 100% | 2018-07-20 | 2018-07-23
614 | No | Content | 2 days | 578SS | 100% | 2018-07-20 | 2018-07-23 | Mktg
615 | No | Design | 2 days | 578SS | 100% | 2018-07-20 | 2018-07-23 | Mktg
616 | No | Functionality | 2 days | 578SS | 100% | 2018-07-20 | 2018-07-23 | Mktg
617 | Yes | Issue Resolution | 7 days | 613SS+1 day | 0% | 2018-07-23 | 2018-07-31 | TCI
618 | Yes | User Acceptance Testing Passed | 2 days | 613 | 0% | 2018-07-24 | 2018-07-25 | Mktg
619 | Yes | Business Owner Signoff | 0 days | 618 | 0% | 2018-07-25 | 2018-07-25 | Mktg
620 | No | Global Elements (consistent across all pages) | 9 days |  | 63% | 2018-07-23 | 2018-08-02
621 | No | Development | 0 days |  | 100% | 2018-07-23 | 2018-07-23
625 | No | In Client Testing | 5 days |  | 100% | 2018-07-24 | 2018-07-30
626 | No | Content | 5 days | 613 | 100% | 2018-07-24 | 2018-07-30 | Mktg
627 | No | Design | 5 days | 613 | 100% | 2018-07-24 | 2018-07-30 | Mktg
628 | No | Functionality | 5 days | 613 | 100% | 2018-07-24 | 2018-07-30 | Mktg
629 | Yes | Issue Resolution | 7 days | 625SS+1 day,621 | 0% | 2018-07-25 | 2018-08-02 | TCI
630 | Yes | User Acceptance Testing Passed | 2 days | 625 | 0% | 2018-07-31 | 2018-08-01 | Mktg
631 | Yes | Business Owner Signoff | 0 days | 630 | 0% | 2018-08-01 | 2018-08-01 | Mktg
632 | Yes | Implicit Submission | 8 days |  | 5% | 2018-07-23 | 2018-08-01
633 | No | Development | 0 days |  | 100% | 2018-07-23 | 2018-07-23
634 | No | Functionality | 0 days |  | 100% | 2018-07-23 | 2018-07-23 | TCI
635 | Yes | In Client Testing | 5 days |  | 15% | 2018-07-23 | 2018-07-27
636 | Yes | Functionality | 5 days | 633 | 15% | 2018-07-23 | 2018-07-27 | Mktg
637 | Yes | Issue Resolution | 7 days | 633,635SS+1 day | 0% | 2018-07-24 | 2018-08-01 | TCI
638 | Yes | User Acceptance Testing Passed | 2 days | 635 | 0% | 2018-07-30 | 2018-07-31 | Mktg
639 | Yes | Business Owner Signoff | 0 days | 638 | 0% | 2018-07-31 | 2018-07-31 | Mktg
640 | No | Phone (Workflow) Application | 9 days |  | 50% | 2018-07-23 | 2018-08-02
641 | No | Development | 0 days |  | 100% | 2018-07-23 | 2018-07-23
645 | No | In Client Testing | 3 days |  | 100% | 2018-07-24 | 2018-07-26
646 | No | Content | 3 days | 625SS,635SS | 100% | 2018-07-24 | 2018-07-26 | Mktg
647 | No | Design | 3 days | 625SS,635SS | 100% | 2018-07-24 | 2018-07-26 | Mktg
648 | No | Functionality | 3 days | 625SS,635SS | 100% | 2018-07-24 | 2018-07-26 | Mktg
649 | Yes | Issue Resolution | 7 days | 645SS+1 day | 0% | 2018-07-25 | 2018-08-02 | TCI
650 | Yes | User Acceptance Testing Passed | 2 days | 645 | 0% | 2018-07-27 | 2018-07-30 | Mktg,LV Ops
651 | Yes | Business Owner Signoff | 0 days | 650 | 0% | 2018-07-30 | 2018-07-30 | Mktg,LV Ops
652 | Yes | Return to Loan | 60 days |  | 95% | 2018-06-22 | 2018-09-17
653 | Yes | Development | 50 days |  | 100% | 2018-06-22 | 2018-08-31
657 | No | In Client Testing | 4 days |  | 100% | 2018-09-04 | 2018-09-07
658 | No | Content | 4 days | 654 | 100% | 2018-09-04 | 2018-09-07 | Mktg
659 | No | Design | 4 days | 654 | 100% | 2018-09-04 | 2018-09-07 | Mktg
660 | No | Functionality | 4 days | 654 | 100% | 2018-09-04 | 2018-09-07 | Mktg
661 | Yes | Issue Resolution | 7 days | 657SS+1 day | 0% | 2018-09-05 | 2018-09-13 | TCI
662 | Yes | User Acceptance Testing Passed | 2 days | 661 | 0% | 2018-09-14 | 2018-09-17 | Mktg
663 | Yes | Business Owner Signoff | 0 days | 662 | 0% | 2018-09-17 | 2018-09-17 | Mktg
664 | Yes | Device Testing | 32 days |  | 68% | 2018-07-09 | 2018-08-21
665 | Yes | Phase 1 | 16 days |  | 100% | 2018-07-09 | 2018-07-30 | Emfluence
666 | No | Distribute Documentation | 1 day | 665 | 100% | 2018-08-06 | 2018-08-06 | Emfluence
667 | Yes | Review Results | 1 day | 666 | 100% | 2018-08-07 | 2018-08-07 | Emfluence,Marketing
668 | No | Identify Defects | 1 day | 667 | 95% | 2018-08-08 | 2018-08-08 | Marketing
669 | Yes | Issue Resolution | 7 days | 668 | 0% | 2018-08-09 | 2018-08-17 | TCI
670 | Yes | User Acceptance Testing Passed | 2 days | 669 | 0% | 2018-08-20 | 2018-08-21 | Marketing
671 | Yes | Business Owner Signoff | 0 days | 670 | 0% | 2018-08-21 | 2018-08-21 | Marketing
672 | Yes | Alight & Has Offers Tasks | 116 days |  | 19% | 2018-04-04 | 2018-09-14
673 | No | Baseline Testing | 5 days |  | 100% | 2018-07-09 | 2018-07-13 | Mktg
674 | No | Gap Analysis | 5 days |  | 100% | 2018-07-09 | 2018-07-13 | Mktg
675 | Yes | Campaign Web Form Development | 116 days |  | 13% | 2018-04-04 | 2018-09-14